THE GENEROSITY ROUNDTABLE  ·  FREE HOST RESOURCE

Community Event RACI Chart

Low-budget events run on borrowed rooms and relationships, so clarity about who owns what does the work a budget usually does. Fill this in with your partners before the event, and keep one chair open.

R Responsible, does the work     A Accountable, owns the outcome (one per row)     C Consulted, weighs in before     I Informed, kept in the loop

| Task | Lead Organizer | Space Partner | Business & Food Partners | Table Host / Facilitator | Volunteers |
| --- | --- | --- | --- | --- | --- |
| BEFORE |  |  |  |  |  |
| Confirm the room, date, and a one-page space agreement | A | R | I | C | I |
| Choose the format (inside, outside, virtual, or hybrid) | A | C | I | R | I |
| Ask local businesses for food and donated product | A | C | R | I | I |
| Registration, invitations, and outreach | A | C | I | C | R |
| Accessibility check (entrances, seating, transit, dietary needs) | A | R | C | C | I |
| Recruit and brief volunteers | A | C | I | C | R |
| DAY OF |  |  |  |  |  |
| Setup, seating in circles, and one open chair | C | A | I | R | R |
| Welcome guests and make introductions | A | I | I | R | R |
| Facilitate the conversation or play | C | I | I | A | I |
| Food and hospitality | C | C | A | I | R |
| Capture what the room learned (notes, photos, quotes) | A | I | I | R | C |
| Reset the room together | A | C | I | R | R |
| AFTER |  |  |  |  |  |
| Thank partners by name, publicly and personally | A | I | I | R | I |
| Follow up with attendees | A | I | I | C | R |
| Debrief: what did we learn, what shifted, what next? | A | C | C | R | C |

Why this chart: at our TogetherTuesday Generosity Roundtable in Cohoes, New York, a board member, a staff fundraiser, and a sixteen-year-old volunteer spent three rounds working through a stalled GivingTuesday campaign. The one tool everyone agreed they needed was a RACI chart. Adapt the roles to your own partners.

generosityspectrum.org  ·  Share freely